## Sheet1
Item | Task | Assigned to | Details | Deadline | Other Committees | Completed
1 | Evaluate Speakers | Donnie | Preview tapes 6:30 Fridays | 2012-10-31
2 | Pick final 3 speakers (Fri, Sat, Sun) | Donnie | Progamming listens to the top 6 speakers and selects best three for final screening by Main Committee | 2012-11-05 | Main Committee
3 | Contact speakers and send confirmation letters | Donnie | Make sure speakers accept engagement. | 2012-11-08
4 | Make speaker airline arrangements | Donnie | Get airport info from speakers and work with Treasurer for payment | 2012-11-30 | Treasurer
5 | Make speaker hotel reservations | Donnie | Verify flight arrivals and inform Hotel & Hosp | 2012-11-30 | Hotel & Hospitality
6 | Complete registration forms for speakers | Donnie | Get info from speakers | 2012-11-30 | Registration
7 | Find hosts for speakers | Donnie | Airport pickup and drop off. Play tour guide. | 2013-02-28 | Convention Guides
8 | Define workshop topics | Marsha & ?? | Submits ideas to programming | 2013-01-20
9 | Confirm 30 workshop speakers | Marsha & ?? | Facilitates getting workshop speakers and sends letters | 2013-02-17
10 | Confirm 30 workshop facilitators | Marsha & ?? | Manages list of volunteers to facilitate workshops | 2013-02-17
11 | Prepare workshop kits | Marsha & ?? | Include PI statement, agenda with timeline, readings, topic, names | 2013-03-17
12 | Marathon Meetings | Open | Arrange for facilitators and formats | 2013-03-17
13 | Fun & Games event | Open | Needs to be developed | 2012-03-17 | ??
14 | Engage and Confirm taping vendor | Robin | Get signed contract. Find out equipment needs. | 2012-09-30 | Jim S.??
15 | Develop programs for main events | Trac | Develop programs for Fri, Sat Banquet & Speaker, Sun. | 2013-03-17 | Arts & Graphics for signage
16 | Develop program for convention | Open | List of all events, times, etc. | ?? | Arts & Graphics
17 | ID Newcomers and Banquet & Entertainment Ticket holders
18 | Transportation from Hotel to DECC and back | Tim & Donnie | How to easily ID for seating, etc. | 2013-02-17 | Hotel & Hospitality; Registration
19 | Banquet Meal Choices | Tim & Donnie | How to easily ID for seating, etc. | 2012-02-17 | Hotel & Hospitality; Registration
20 | Seating arrangements banquet, main speaker, entertainment | Tim & Donnie | Figure out logistics and oversee during event | 2013-02-17 | Hotel & Hospitality; Arts & Graphics
21 | Podium & PA needs all events | Tim & Donnie | Figure out logistics and oversee during event | 2013-02-17 | Hotel & Hospitality
22 | Reset of Lyric Room after breakfast | Tim & Donnie | Figure out logistics and oversee during event | 2013-02-17 | Hotel & Hospitality
23 | Reset of all rooms for speaker & workshops at Hotel | Tim & Donnie | Figure out logistics and oversee during event | 2013-02-17 | Hotel & Hospitality
24 | Cleantime countdown | Tim & Donnie | Figure out logistics and oversee during event | 2013-02-17
25 | Get free CDs from Tapeman | Robin | Label as a surprise gift and drop randumly in reg pkgs | 2013-03-17 | Registration
26 | Medalion Hunt | Spence | Organize medalion hunt. Tape set for prize | 2013-03-17
27 | Signage | Open | Workshops, Marathon, Agenda, Directional, Programs | 2013-03-01 | Arts & Graphics
28
29
30
31
32
33
34
35
36
37
38
39
40