Project Plan

UMSO Audit

Status:  Proposed

Version:  0.1

Prepared by:  Jeff Spencer

Project Manager:  TBD

Date Created:  10/29/2011

Date Last Revised:  11/19/2011

Document Revision History

| Version # | Date | Requestor | Revised By | Change Description |
| --- | --- | --- | --- | --- |
| 0.1 | 10/29/11 | MNRSC | Jeff Spencer | Initial Project Plan Draft |

- Project Scope

  - Project Purpose

Questions regarding the financial stability of the Upper Midwest Service Office have arisen because recently the UMSO requested a donation from the MNRSC for $3,000.  The UMSO has not been providing regular financial reports to the MNRSC, and inconsistencies of inventory values have been reported by NA members.

NA’s Eleventh Concept states, “NA funds are to be used to further our primary purpose, and must be managed responsibly.”   Accountability is an essential aspect of responsible NA financial management.  Regular financial reports, open books, and periodic audits of NA accounts help our members be sure their contributions are being used well. Consistent financial records help us make realistic spending plans for future service activities.

  - Project Objective

There are four high-level objectives:

- Perform a complete audit of UMSO financial records for 2011.

- Obtain a current net worth.

- Identify a five-year trend of high-level financial metrics.

- Create business projections through 2016.

  - Project Benefits

- NA members will have confidence in the accuracy of the Upper Midwest Service Office’s financial position

- The MNRSC will be able to make good decisions regarding service priorities and ensure the long-term viability of the service office.

  - Long Term Goals

- To be a trustworthy leader with the foresight to identify trends and issues affecting the fellowship and the ability to develop innovative solutions to address them

- To provide products and services that meet the changing needs of the Region.

- To foster unity of purpose and a keen sense of mutual accountability and support.

- To be an organization characterized by integrity and consistency, whose words and actions are driven by spiritual principles contained in the 12 Steps, 12 Traditions, and 12 Concepts.

- To build productive partnerships throughout our Region to fulfill our vision: relationships with other components of the service structure, local NA communities, and between committees and boards.

- To be a model of service by setting high standards, being efficient in operations, avoiding needless duplication of services, and an unwavering focus on the needs of those we serve.

- To be responsive and accessible, inviting involvement and dialogue, and ensuring efficient delivery of services.

- To be a sound organization with the structure and capacity, human and financial, to achieve our goals and priorities.

- Inclusions and Exclusions

Inclusions

- Internal Audit

- Business projections

Exclusions

- Not applicable

- Project Impacts

  - Key Assumptions

This project will be led and completed by Regional Committee Members.

  - Key Critical Success Factors

| Critical Success Factor | Key Success Indicator |
| --- | --- |
| RCMs complete a full audit of 2011 books | Audit complete |
| RCMs complete a full inventory count | Inventory count complete |
| RCMs record key historical metrics | Historical metrics obtained |
| RCMs create 5-year business projections | Business projections created |

- Project Steps

| Key Deliverables / Milestones | Assigned To | Planned Start Date | Planned Completion Date | Actual Completion Date |
| --- | --- | --- | --- | --- |
| Project initiation approval | MNRSC | 10/08/11 | 10/08/11 | 10/08/11 |
| Project plan approval | MNRSC | 12/10/11 | 12/10/11 |  |
| Project manager assignment | MNRSC | 12/10/11 | 12/10/11 |  |
| Project team recruitment | PM | 12/10/11 | 12/10/11 |  |
| Review audit procedures | Team | 12/10/11 | 12/17/11 |  |
| Set audit and inventory appointments with UMSO Board | PM | 12/10/11 | 12/17/11 |  |
| Complete inventory | Team | 12/17/11 | 12/31/11 |  |
| Complete audit | Team | 01/01/12 | 01/15/12 |  |
| Complete business projections | Team | 01/15/12 | 01/31/12 |  |

- Budget Estimate

| EXPENSES TO IMPLEMENT PROJECT |  |  |
| --- | --- | --- |
| Travel Expenses |  | $100 |
| Total Project Estimated Expenses |  | $100 |

- Roles & Responsibilities

| Role | Name | Responsibilities |
| --- | --- | --- |
| Project Manager | TBD | Team lead |
| Project Sponsor | Jeff Spencer | FST Member |
| Team Member |  |  |
| Team Member |  |  |
| Team Member |  |  |

- Attachments

- Detailed Audit objectives

- Grant Thornton Not-for-profit Audit Committee Handbook

- Approvals

Review and Approve

| Name | Position | Review/Approval Results, Date | Approval Method |
| --- | --- | --- | --- |
| Jeff Spencer | MNRSC Chair |  |  |
| Monte Jarvis | MNRSC Treasurer |  |  |
| Kit Egan | MNRSC Secretary |  |  |
| Caleb Black | MNRSC Regional Delegate |  |  |
| Anthony Benedetti | MNRSC Regional Delegate Alt |  |  |
| Jay Sawatsky | MNRSC FST |  |  |
| MNRSC | Regional Conference |  |  |

# UMSO Detailed Audit Objectives

- Review internal controls

- Identify business risks

- Review accounting policies & procedures

- Validate random sample of expense transactions vs. receipts

- Validate random sample of sales transactions vs. invoices

- Balance bank statements

- Obtain copies of 990 filings from 2007-2011

- Obtain copies of annual reports from 2007-2011

- Count all inventory: Determine the following values for each inventory item

- Average cost

- Expected count

- Actual count

- Average cost X Actual cost

- Variance between expected and actual count

- Average cost X variance

- UMSO retail price

- NAWS retail price

- Variance between UMSO and NAWS retail price