| Tasks | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Event |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Review Financial Reports | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Pay Annual Storage Fee | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Vote in Committee Members | X | X |  |  |  |  |  |  |  |  |  |  |  |
| Evaluate PO Box/Bank Account |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Review Bylaws |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Vote on Bylaw Changes |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Vote on Slogan/Logo |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Select T-shirt Vendor |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Vote on Gate Pricing |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Vote on T-shirt Prices |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Create Flyers |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Pay Annual PO Box Fee |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Select T-shirt Options/Prices |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Update Square Items/Pricing |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Create Winner Certificates |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Discuss Donations to Events |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Online Registration Set-up |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Solicit Music Bids |  |  |  |  |  | X | X |  |  |  |  |  |  |
| Contact Meat Vendor |  |  |  |  |  | X | X |  |  |  |  |  |  |
| Meet with Campground |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Approve Campground Contract |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Chili Feed Pricing/Sales |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Select Music |  |  |  |  |  |  | X | X |  |  |  |  |  |
| Obtain Insurance Coverage |  |  |  |  |  |  |  | X | X |  |  |  |  |
| Reserve Table/Chairs |  |  |  |  |  |  |  | X | X |  |  |  |  |
| Contact Treatment Centers |  |  |  |  |  |  |  | X | X |  |  |  |  |
| Schedule Storage Inventory |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Speaker Suggestions |  |  |  |  |  |  |  |  | X | X |  |  |  |
| Collect Raffle Items |  |  |  |  |  |  |  |  | X | X | X | X |  |
| Order Needed Inventory |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Confirm Raffle Ticket Prices |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Speaker Selections |  |  |  |  |  |  |  |  |  | X | X |  |  |
| Confirm Gate/Merch. Hours |  |  |  |  |  |  |  |  |  |  | X |  |  |
| Update Schedule of Events |  |  |  |  |  |  |  |  |  |  | X |  |  |
| Print Activity Sign-up Sheets |  |  |  |  |  |  |  |  |  |  | X |  |  |
| Print Volunteer Sign-up Sheets |  |  |  |  |  |  |  |  |  |  | X |  |  |
| Order Continental Breakfast |  |  |  |  |  |  |  |  |  |  | X |  |  |
| Order Corn & Buns |  |  |  |  |  |  |  |  |  |  | X |  |  |
| Order Sam’s Club Items |  |  |  |  |  |  |  |  |  |  |  | X |  |
| Purchase Basic Texts |  |  |  |  |  |  |  |  |  |  |  | X |  |